## Sheet1
User Story | Priority | Estimated time | Person Assigned | Sprint assigned
As a manager I want to be able to add users to the system | High | 3 | Will
As a user I want to be able to log in to the system | High | 3 | Liam
As a user I want to be able to change my password | Low | 3 | Liam
As a manager I want to be able to add customer info such as name, address, and price | High | 4 | Will
As a user I want to be able to add delivery information such as date, number of bags, and if they paid with cash, check, or didn't pay | High | 4
As a manager I want to be able to change customer info | Med | 4
As a manager I want to be able to see reports on customers by month/year | Med | 5
As a manager I want to be able to see total sales reports by month/year | Med | 5
As a user I want to be able to add my hours worked | Med | 3
As a manager I want to be able to see hours that users have worked and mark them as paid | Med | 4
As a manager I want to be able to see reports on hours worked by user | Low | 5